## READ ME
AMLR readiness workbook
About this template |  |  | Group | Status | Dependency status | Instrument type | Owner role | Plan status | Changelog type
What it is for | A readiness workbook for Regulation (EU) 2024/1624 (the AMLR), which applies from 10 July 2027: 14 workstreams, each with the AMLR article, what the law requires, what to do before 10 July 2027, the owner by role, the evidence an examiner will sample and the AMLA instrument it waits on, plus a tracker of AMLA's standards and a 90-day plan. |  | Governance and risk assessment | Not started | Final draft with the Commission | RTS | Board / management body | Not started | Row added
Sheets | READ ME (this sheet, with the dropdown lists in columns E to K); Readiness checklist (14 worked rows, one per workstream); AMLA standards tracker (12 rows from the article, with the nine 2027 guideline mandates split out underneath); 90-day plan (four windows from 6 October 2026 to 3 January 2027); Changelog (who changed what, when and why). |  | Customer due diligence | In progress: red | Consultation closed | ITS | Compliance manager | In progress | Row changed
Related article | https://www.regwatch.io/blog/eu-amlr-readiness-checklist |  | Groups, third parties, reporting and records | In progress: amber | Consultation open | Guidelines | CCO | Done | Status change
Version | Prepared by RegWatch, 5 October 2026 |  |  | In progress: green | Consultation planned | Commission delegated act | Compliance officer (MLRO) | Slipped | Dependency change
As of | Every status, date and dependency in the worked rows was checked against the primary source linked on its row as of 5 October 2026. |  |  | Complete | Pre-consultation engagement | National law | Head of financial crime risk (2LOD) |  | Source update
Legal note | This template is general information, not legal advice. |  |  | Not applicable | Not yet consulted on | National guidance | Head of KYC operations (1LOD) |  | Structural change
[5 empty] | Not yet published |  | Screening lead
How to use it |  |  |  |  | Adopted, awaiting Official Journal |  | Head of transaction monitoring
One row per workstream | The 14 checklist rows are the minimum. Split a row when two owners or two deadlines would otherwise share it; never merge rows. |  |  |  | Published in the Official Journal |  | Group CCO
Name a person | Column 8 holds a named person. The role in column 7 is the default; a row without a named person is a finding in itself. |  |  |  | Applies |  | COO
Keep the evidence column honest | Column 9 lists what an examiner is likely to sample. Put the location of each artifact in column 16 and test that you can produce it within 48 hours. |  |  |  | No dependency |  | CFO
Follow the dependencies | Column 10 names the AMLA instrument each row waits on and column 11 its status. When the tracker sheet changes, update column 11 here and log it on the Changelog. | [5 empty] | DPO
Not applicable needs a reason | Status "Not applicable" (column 15) requires a justification in column 19 and a last-reviewed date in column 18. | [5 empty] | Head of records
Keep rows fresh | Column 18 (Last reviewed) turns amber after 90 days on the checklist; on the tracker, column 12 turns amber after 30 days. | [5 empty] | HR
Edit the dropdowns | The options live in columns E to K of this sheet. Insert a cell inside a list to add an option so the range grows with it. | [5 empty] | Internal audit
Cadence
When AMLA, the Commission or your supervisor publishes | Log the publication on the Changelog, update the tracker row and every linked checklist row, and re-date them.
Monthly | Re-check every tracker row against its source URL and update columns 6, 7 and 12; review RAG status, dependency status and target dates with the workstream owners.
Quarterly | Re-check every checklist row against its AMLR article and AMLA source, and update column 18.
Before each board meeting | Fill the "Board readiness update" section of this sheet from the checklist.
Key dates
Date | What happens | Basis
2026-07-10 | Deadline for AMLA's first AMLR standards and guidelines; member states transpose AMLD6's rules on access to beneficial ownership registers | AMLR Arts. 9(4), 10(4), 16(4), 17(3), 19(9), 20(3), 26(5), 28(1), 69(3); AMLD6 Art. 78
2026-10-01 | AMLA publishes final draft RTS on CDD, linked transactions and group-wide requirements | AMLA
2026-12-31 | Reference date for the data AMLA uses to select entities for direct supervision | Draft ITS under AMLA Regulation Art. 15(3), Art. 5
2027-03-31 | National supervisors finish collecting that data from provisionally eligible entities | Same draft ITS, Art. 5(3)
By 1 Jul 2027 | AMLA starts its first selection, which must conclude within six months | AMLA Regulation Art. 13(4)
2027-07-10 | AMLR applies; AMLD6 transposition deadline; the Fourth AML Directive is repealed | AMLR Art. 90; AMLD6 Arts. 77, 78
2028 | AMLA starts direct supervision, six months after publishing its list of selected entities | AMLA Regulation Art. 13(4); AMLA timeline
2029-07-10 | AMLR applies to football agents and professional football clubs; voting and distribution rights on unconverted bearer shares are suspended | AMLR Arts. 90, 79(3)
Board readiness update
1. Headline | overall RAG status and the date the AMLR applies, 10 July 2027.
2. Workstreams | the 14 rows with RAG status, owner and next milestone.
3. Decisions needed now | the compliance manager appointment (Article 11(1)), remediation funding, outsourcing changes, and for groups the EU parent undertaking.
4. External dependencies | AMLA instruments still pending, with AMLA's own planned dates.
5. AMLA selection | eligibility status, and the 31 March 2027 data deadline if it applies.
6. Top three risks | for example the CDD data model, vendor contracts and staffing, each with its mitigation.
7. Evidence readiness | what an examiner could sample today, row by row.
8. Next update | the date, and what will have changed by then.
Readiness checklist columns
1. Ref | A stable ID, CHK-01 to CHK-14 for the worked rows; never reuse an ID.
2. Group | The article section the row sits under.
3. Workstream | The workstream name exactly as in the article.
4. AMLR basis | The articles of the AMLR (or AMLA Regulation) the row rests on.
5. What the AMLR requires | The legal requirement in plain words; quote the article when in doubt.
6. Do before 10 July 2027 | The actions that close the gap before the AMLR applies.
7. Owner (role) | The accountable role.
8. Named owner | The person accountable for the row; blank is a finding.
9. Evidence an examiner will sample | The artifacts a supervisor or auditor is likely to ask for.
10. Waiting on | The AMLA instrument (or none) that may change the row.
11. Dependency status | The status of the instrument in column 10, matching the tracker sheet.
12. Linked tracker rows | Tracker refs (TRK-xx) for the instruments in column 10.
13. Source URL | The primary source for the AMLR basis (EUR-Lex article anchor).
14. Dependency source URL | The AMLA page or document for the instrument in column 10.
15. Status | RAG status of the workstream; Not applicable needs a reason in column 19.
16. Evidence location | Where the evidence in column 9 is kept.
17. Target date | When the actions in column 6 will be complete.
18. Last reviewed | When a human last checked the row against its sources; amber after 90 days.
19. Notes and justification | Decisions, assumptions and any Not applicable reasoning.
AMLA standards tracker columns
1. Ref | A stable ID, TRK-01 onward; child rows use a letter suffix.
2. Instrument | The AMLA (or AMLA and EDPB) instrument, named as in the article.
3. Type | RTS, ITS or guidelines.
4. Basis and legal due date | The mandate article and the date the law set for AMLA, as in the article.
5. Legal due date | The statutory deadline as a date, for sorting.
6. Status on 5 Oct 2026 | The status in words, as of the date in the header; rename the header when you re-date the sheet.
7. Status code | The status as a code, used by the checklist sheet.
8. What it means for your build | What to build or change now because of this instrument.
9. Linked checklist rows | CHK refs whose column 10 names this instrument.
10. Source URL | The AMLA page or document that proves the status.
11. Next check date | When someone will next check the source; default 30 days out, or the planned date AMLA gives.
12. Last reviewed | When a human last checked the row; amber after 30 days.
90-day plan columns
1. Window | The window as written in the article.
2. Start | First day of the window.
3. End | Last day of the window.
4. Actions | What gets done in the window.
5. Owner | The accountable roles; add names.
6. Output | The artifact that proves the window is done.
7. Status | Not started, In progress, Done or Slipped.
8. Done date | When the output was accepted.
9. Notes | Slippage reasons and decisions.
Primary sources
AMLR, Regulation (EU) 2024/1624 | https://eur-lex.europa.eu/eli/reg/2024/1624/oj
AMLD6, Directive (EU) 2024/1640 | https://eur-lex.europa.eu/eli/dir/2024/1640/oj
AMLA Regulation, Regulation (EU) 2024/1620 | https://eur-lex.europa.eu/eli/reg/2024/1620/oj
AMLA regulatory instruments (last updated 30 September 2026) | https://www.amla.europa.eu/policy/regulatory-instruments_en
AMLA public consultations | https://www.amla.europa.eu/policy/public-consultations_en
AMLA press release, 1 October 2026 | https://www.amla.europa.eu/press-release-amla-finalises-key-standards-private-sector_en
AMLA work programme, Annex XI planning | https://www.amla.europa.eu/document/download/5ac4c728-9b4e-4416-b469-030f3fe32ce2_en?filename=Annex%20XI%20to%20AMLA%20SPD%202026-2028.pdf

## Readiness checklist
1. Ref | 2. Group | 3. Workstream | 4. AMLR basis | 5. What the AMLR requires | 6. Do before 10 July 2027 | 7. Owner (role) | 8. Named owner | 9. Evidence an examiner will sample | 10. Waiting on | 11. Dependency status | 12. Linked tracker rows | 13. Source URL | 14. Dependency source URL | 15. Status | 16. Evidence location | 17. Target date | 18. Last reviewed | 19. Notes and justification
CHK-01 | Governance and risk assessment | 1. Governance and roles | Arts. 9, 11 | Written policies approved by the management body; procedures approved at least by the compliance manager; a compliance manager and a compliance officer; an annual report | Appoint the compliance manager by board resolution; confirm the compliance officer's standing and removal process; re-paper approvals; diary the annual report | Company secretary with the CCO |  | Board minutes naming both roles; approval trail per document; the annual report and the board's response | Compliance staffing guidelines (Art. 9(4)), planned for 2027 | Not yet consulted on | TRK-08 | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_11 | https://www.amla.europa.eu/document/download/5ac4c728-9b4e-4416-b469-030f3fe32ce2_en?filename=Annex%20XI%20to%20AMLA%20SPD%202026-2028.pdf |  |  |  | 2026-10-05
CHK-02 | Governance and risk assessment | 2. Business-wide risk assessment | Art. 10 | A documented assessment of ML/TF and sanctions-evasion risk, drawn up by the compliance officer, approved by the management body, kept up to date; new products assessed before launch | Rebuild the methodology on the draft guidelines' four minimum requirements; add sanctions-evasion risk; link each residual risk to controls and remediation; set review triggers | Compliance officer (MLRO) |  | Methodology with weighting rationale; dated, approved assessment; sources list; pre-launch product assessments | BWRA guidelines (Art. 10(4)), consultation closed | Consultation closed | TRK-04 | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_10 | https://www.amla.europa.eu/policy/public-consultations/consultation-draft-guidelines-business-wide-risk-assessment_en |  |  |  | 2026-10-05
CHK-03 | Governance and risk assessment | 3. Customer risk assessment | Art. 20(2), (4); Annexes I to III | CDD measures set by an individual risk analysis using the Annex I variables and Annex II and III factors; ability to show the measures fit the risk | Map the risk model's factors to Annexes I to III; document weights and overrides; test that ratings drive simplified, standard or enhanced measures | Head of financial crime risk (2LOD) |  | Model documentation; factor mapping; override log; files where rating and measures match | Risk factor guidelines (Art. 20(3)), not yet consulted on | Not yet consulted on | TRK-07 | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_20 | https://www.amla.europa.eu/policy/regulatory-instruments_en |  |  |  | 2026-10-05
CHK-04 | Customer due diligence | 4. CDD data model and remediation of existing files | Arts. 19, 20, 22, 23, 25, 26(2) | Fixed identification data; verification by documents, reliable sources or eIDAS e-ID; purpose and intended nature; customer information updated within one year (higher risk) or five | Gap the onboarding data model field by field against Art. 22 and the final draft RTS; count the existing book by risk band; plan remediation within the one-year and five-year windows | Head of KYC operations (1LOD) |  | Field-level gap analysis; remediation plan with population counts and dates; sampled customer files | CDD RTS (Art. 28(1)), final draft with the Commission | Final draft with the Commission | TRK-01; TRK-02 | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_22 | https://www.amla.europa.eu/document/download/e15ab2e5-4074-4de8-bb9d-613dd8b7fdd1_en?filename=Final%20Report%20-%20draft%20RTS%2028%281%29%20AMLR.pdf |  |  |  | 2026-10-05
CHK-05 | Customer due diligence | 5. Beneficial ownership | Arts. 20(1)(b), 22(7), 23(4), 24, 51 to 55, 67(4) | Owners at 25% or more, multiplied through chains, plus control via other means; verification beyond the central register; discrepancies reported within 14 calendar days | Re-run ownership logic for exactly 25% and indirect chains; add control questions; build the 14-day discrepancy workflow; collect proof of registration at onboarding | Head of KYC operations |  | Ownership charts with calculations; dated discrepancy reports; records where no owner was found | CDD RTS (verification sources) | Final draft with the Commission | TRK-01 | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_51 | https://www.amla.europa.eu/document/download/e15ab2e5-4074-4de8-bb9d-613dd8b7fdd1_en?filename=Final%20Report%20-%20draft%20RTS%2028%281%29%20AMLR.pdf |  |  |  | 2026-10-05
CHK-06 | Customer due diligence | 6. Politically exposed persons | Arts. 2(1)(34) to (36), 20(1)(g), 42 to 46 | PEP, family member and close associate checks; senior management approval, source of wealth and funds, enhanced monitoring; measures for at least 12 months after office ends | Extend lists to regional and local office holders and siblings of top officials; re-screen when the EU list of prominent functions changes; check insurance beneficiaries at payout | Screening lead with the MLRO |  | Screening configuration and list coverage; approval records; source-of-wealth files | PEP guidelines (Art. 42(2)), due 10 Jul 2027; CDD RTS (screening) | Not yet published | TRK-01; TRK-10b | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_42 | https://www.amla.europa.eu/policy/regulatory-instruments_en |  |  |  | 2026-10-05
CHK-07 | Customer due diligence | 7. Enhanced due diligence and high-risk third countries | Arts. 29 to 31, 34 to 39, 41 | Enhanced measures in higher-risk cases and for third countries the Commission identifies by delegated act; scrutiny of complex or unusually large transactions | Make country lists follow Commission delegated acts; define EDD menus from Art. 34(4); flag higher-risk customers with EUR 50 million or more in assets for Art. 34(5) | MLRO |  | EDD files with senior management approval; Art. 34(2) transaction reviews; country list change log | Geographic risk (Art. 32) and wealth-test (Art. 34(5)) guidelines, due 10 Jul 2027 | Not yet published | TRK-10g; TRK-10h | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_34 | https://www.amla.europa.eu/policy/regulatory-instruments_en |  |  |  | 2026-10-05
CHK-08 | Customer due diligence | 8. Ongoing monitoring | Art. 26 | Monitoring of transactions against the customer profile; current customer data; sanctions checks, for credit and financial institutions on every new designation | Map scenarios to the BWRA; assess vendor default settings; validate automated alert closure by sampling; re-screen on new designations; use group data on shared customers | Head of transaction monitoring |  | Scenario inventory and tuning records; alert-to-case-to-report outcomes; QA samples of closed alerts | Monitoring guidelines (Art. 26(5)), consultation closed | Consultation closed | TRK-05 | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_26 | https://www.amla.europa.eu/policy/public-consultations/consultation-draft-guidelines-ongoing-monitoring-business-relationship_en |  |  |  | 2026-10-05
CHK-09 | Groups, third parties, reporting and records | 9. Group-wide policies and information sharing | Arts. 16, 17, 73(3) | A group-wide risk assessment, group policies (including data protection and information sharing) and a group compliance manager; third-country branches and subsidiaries of EU groups meet AMLR standards | Identify the parent undertaking; build the group assessment from entity assessments; set sharing rules for customer, ownership and suspicion data; list third-country legal impediments | Group CCO |  | Approved group policy set; group-wide risk assessment; sharing protocol and logs; parent notification (non-EU groups) | Group-wide RTS (Arts. 16(4), 17(3)), final draft with the Commission | Final draft with the Commission | TRK-03 | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_16 | https://www.amla.europa.eu/document/download/ffcb26fd-0a0e-4f4f-9c3d-9f3ce0a283b5_en?filename=Final%20Report%20-%20draft%20RTS%2016%284%29%20and%2017%283%29%20AMLR.pdf |  |  |  | 2026-10-05
CHK-10 | Groups, third parties, reporting and records | 10. Outsourcing and reliance | Arts. 18, 48 to 50 | Supervisor notified before a provider starts an AML task; six tasks never outsourced; reliance under a written agreement with CDD data supplied within 5 working days | Inventory every AML task run by a vendor or group entity; test it against Art. 18(3); prepare notifications; re-paper contracts; test reliance data delivery | COO with the MLRO |  | Outsourcing register; supervisor notifications; agreements; provider control testing; reliance test results | Outsourcing (Art. 18(8)) and reliance (Art. 50) guidelines, due 10 Jul 2027 | Not yet published | TRK-10a; TRK-10c | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_18 | https://www.amla.europa.eu/policy/regulatory-instruments_en |  |  |  | 2026-10-05
CHK-11 | Groups, third parties, reporting and records | 11. FIU reporting | Arts. 69 to 74, 80(4) | Prompt suspicion reports by the compliance officer; FIU requests answered within 5 working days; suspect transactions held until reported; no tipping off; threshold reports where relevant | Re-time FIU responses to 5 working days; record every Art. 69(2) assessment, including decisions not to report; map case data to the common reporting format | MLRO |  | Report register with timestamps; FIU request log with response times; records of no-report decisions | Reporting format ITS (Art. 69(3)), consultation closed; indicator guidelines (Art. 69(5)) | Consultation closed | TRK-06; TRK-10d | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_69 | https://www.amla.europa.eu/policy/public-consultations/consultation-draft-its-format-reporting-suspicions-and-providing-transaction-records_en |  |  |  | 2026-10-05
CHK-12 | Groups, third parties, reporting and records | 12. Record keeping and data protection | Arts. 76 to 78 | Unredacted CDD records, suspicion assessments and transaction records kept 5 years after the relationship ends, then deleted; systems to answer FIU enquiries; meaningful human intervention in automated decisions | Set retention to the AMLR clock with deletion; test retrieval for FIU enquiries; document human review points in automated onboarding and monitoring decisions | Head of records with the DPO and MLRO |  | Retention schedule; deletion logs; retrieval test results; data protection impact assessments | None: the AMLR text applies | No dependency |  | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_77 |  |  |  |  | 2026-10-05
CHK-13 | Groups, third parties, reporting and records | 13. Training and staff integrity | Arts. 12, 13 | Specific, ongoing training appropriate to functions and risks, duly documented; skills and integrity assessments for staff in AML roles before they start and repeated | Build role-based curricula from the BWRA's top risks; record results by role; run Art. 13 assessments for staff, agents and distributors | MLRO with HR |  | Training needs analysis tied to the BWRA; role-based materials; results by role; Art. 13 assessment records | None: the AMLR text applies | No dependency |  | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_12 |  |  |  |  | 2026-10-05
CHK-14 | Groups, third parties, reporting and records | 14. AMLA selection readiness | AMLA Regulation Arts. 12, 13 | Credit and financial institutions operating in at least six member states are assessed for direct supervision on data as of 31 Dec 2026 | Count member states as AMLA will; if provisionally eligible, name a data owner, reconcile data points with the BWRA and rehearse the submission (collection closes 31 Mar 2027) | CCO with the CFO |  | Eligibility calculation; data lineage; submission sign-off | Selection RTS (AMLA Regulation Art. 12(7)) and cooperation ITS (Art. 15(3)), final drafts | Final draft with the Commission |  | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1620#art_12 | https://www.amla.europa.eu/document/download/523b7780-4035-40c4-9d64-f1947ca0259a_en?filename=Final%20report%20-%20ITS%20under%20Article%2015%283%29%20AMLAR.pdf |  |  |  | 2026-10-05

## AMLA standards tracker
1. Ref | 2. Instrument | 3. Type | 4. Basis and legal due date | 5. Legal due date | 6. Status on 5 Oct 2026 | 7. Status code | 8. What it means for your build | 9. Linked checklist rows | 10. Source URL | 11. Next check date | 12. Last reviewed
TRK-01 | RTS on customer due diligence | RTS | Art. 28(1); 10 Jul 2026 | 2026-07-10 | Final draft submitted to the Commission (1 Oct 2026); applies six months after entry into force | Final draft with the Commission | Freeze the CDD data model on it: names and place of birth as on the ID document, structured addresses, a low-risk data set without address, e-ID attributes, alternative non-face-to-face checks, PEP and sanctions screening | CHK-04; CHK-05; CHK-06 | https://www.amla.europa.eu/document/download/e15ab2e5-4074-4de8-bb9d-613dd8b7fdd1_en?filename=Final%20Report%20-%20draft%20RTS%2028%281%29%20AMLR.pdf |  | 2026-10-05
TRK-02 | RTS on business relationships, occasional and linked transactions | RTS | Art. 19(9); 10 Jul 2026 | 2026-07-10 | Final draft submitted (1 Oct 2026); no lower CDD thresholds beyond the AMLR's own | Final draft with the Commission | Remitters, bureaux de change and crypto exchange and transfer services: three or more transactions in 12 months indicate a relationship, and a one-month window applies to linking | CHK-04 | https://www.amla.europa.eu/document/download/32e5aea0-52dc-4b0c-b93a-b0dd373fcd0f_en?filename=Final%20Report%20-%20draft%20RTS%20under%20Article%2019%289%29%20AMLR.pdf |  | 2026-10-05
TRK-03 | RTS on group-wide requirements and third-country measures | RTS | Arts. 16(4), 17(3); 10 Jul 2026 | 2026-07-10 | Final draft submitted (1 Oct 2026) | Final draft with the Commission | Group framework, information-sharing annex, EU parent notification within 28 days and approval within 60; repeals Delegated Regulation (EU) 2019/758 from 10 Jul 2027 | CHK-09 | https://www.amla.europa.eu/document/download/ffcb26fd-0a0e-4f4f-9c3d-9f3ce0a283b5_en?filename=Final%20Report%20-%20draft%20RTS%2016%284%29%20and%2017%283%29%20AMLR.pdf |  | 2026-10-05
TRK-04 | Guidelines on the business-wide risk assessment | Guidelines | Art. 10(4); 10 Jul 2026 | 2026-07-10 | Consultation ran 16 Apr to 15 Jul 2026; final text pending | Consultation closed | Four minimum requirements: business overview, inherent risk, control quality, residual risk | CHK-02 | https://www.amla.europa.eu/policy/public-consultations/consultation-draft-guidelines-business-wide-risk-assessment_en |  | 2026-10-05
TRK-05 | Guidelines on ongoing monitoring | Guidelines | Art. 26(5); 10 Jul 2026 | 2026-07-10 | Consultation ran 3 Jun to 3 Sep 2026; final text pending | Consultation closed | Documented assessment of vendor default settings, human oversight of automated alert closure, effectiveness measured by outcomes | CHK-08 | https://www.amla.europa.eu/policy/public-consultations/consultation-draft-guidelines-ongoing-monitoring-business-relationship_en |  | 2026-10-05
TRK-06 | ITS on the format for reporting suspicions | ITS | Art. 69(3); 10 Jul 2026 | 2026-07-10 | Consultation ran 2 Jul to 20 Sep 2026; application date left open in the draft | Consultation closed | A common core data set with templates by type of obliged entity; firms that automate filing instead of using their FIU's platform must build to them | CHK-11 | https://www.amla.europa.eu/policy/public-consultations/consultation-draft-its-format-reporting-suspicions-and-providing-transaction-records_en |  | 2026-10-05
TRK-07 | Guidelines on risk variables and risk factors | Guidelines | Art. 20(3); 10 Jul 2026 | 2026-07-10 | Not yet consulted on | Not yet consulted on | Keep the customer risk model mapped to the EBA's ML/TF Risk Factors Guidelines, which still apply | CHK-03 | https://www.amla.europa.eu/policy/regulatory-instruments_en |  | 2026-10-05
TRK-08 | Guidelines on internal policies and compliance staffing | Guidelines | Art. 9(4); 10 Jul 2026 | 2026-07-10 | Not yet consulted on; AMLA's work programme plans a consultation in Q1 2027 and a final text in Q2 2027 | Not yet consulted on | Size the compliance functions on your own documented analysis for now | CHK-01 | https://www.amla.europa.eu/document/download/5ac4c728-9b4e-4416-b469-030f3fe32ce2_en?filename=Annex%20XI%20to%20AMLA%20SPD%202026-2028.pdf |  | 2026-10-05
TRK-09 | Guidelines on simplified due diligence (AMLA's own initiative) | Guidelines | Art. 33; no legal due date | None | Roundtables in Frankfurt, 9 Nov to 2 Dec 2026 (expressions of interest by 18 Oct); AMLA says a public consultation will follow | Pre-consultation engagement | Design SDD on Art. 33 and the CDD RTS only | CHK-04 | https://www.amla.europa.eu/amla-invites-stakeholders-sectoral-roundtables-simplified-customer-due-diligence_en |  | 2026-10-05
TRK-10 | Nine guidelines due by 10 Jul 2027: outsourcing, PEPs, reliance, suspicious activity indicators, self-hosted addresses, CASP correspondents, geographic risk, the EUR 50 million wealth test, de-risking (joint with the EBA) | Guidelines | Arts. 18(8), 42(2), 50, 69(5), 40(2), 37(3), 32(1), 34(5), 21(4) | 2027-07-10 | None published | Not yet published | Build to the AMLR text and diary a re-check for each | CHK-06; CHK-07; CHK-10; CHK-11 | https://www.amla.europa.eu/policy/regulatory-instruments_en |  | 2026-10-05
TRK-10a | Guidelines on outsourcing | Guidelines | Art. 18(8); 10 Jul 2027 | 2027-07-10 | None published | Not yet published | Build to the AMLR text and diary a re-check | CHK-10 | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_18 |  | 2026-10-05
TRK-10b | Guidelines on politically exposed persons | Guidelines | Art. 42(2); 10 Jul 2027 | 2027-07-10 | None published | Not yet published | Build to the AMLR text and diary a re-check | CHK-06 | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_42 |  | 2026-10-05
TRK-10c | Guidelines on reliance on other obliged entities | Guidelines | Art. 50; 10 Jul 2027 | 2027-07-10 | None published | Not yet published | Build to the AMLR text and diary a re-check | CHK-10 | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_50 |  | 2026-10-05
TRK-10d | Guidelines on indicators of suspicious activity or behaviors | Guidelines | Art. 69(5); 10 Jul 2027 | 2027-07-10 | None published | Not yet published | Build to the AMLR text and diary a re-check | CHK-11 | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_69 |  | 2026-10-05
TRK-10e | Guidelines on transfers with self-hosted addresses | Guidelines | Art. 40(2); 10 Jul 2027 | 2027-07-10 | None published | Not yet published | Build to the AMLR text and diary a re-check | CHK-07 | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_40 |  | 2026-10-05
TRK-10f | Guidelines on cross-border correspondent relationships for CASPs | Guidelines | Art. 37(3); 10 Jul 2027 | 2027-07-10 | None published | Not yet published | Build to the AMLR text and diary a re-check | CHK-07 | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_37 |  | 2026-10-05
TRK-10g | Guidelines on ML/TF risks, trends and methods outside the Union (geographic risk) | Guidelines | Art. 32(1); 10 Jul 2027 | 2027-07-10 | None published | Not yet published | Build to the AMLR text and diary a re-check | CHK-07 | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_32 |  | 2026-10-05
TRK-10h | Guidelines on establishing total assets of EUR 50 million (the wealth test) | Guidelines | Art. 34(5); 10 Jul 2027 | 2027-07-10 | None published | Not yet published | Build to the AMLR text and diary a re-check | CHK-07 | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_34 |  | 2026-10-05
TRK-10i | Joint guidelines with the EBA on de-risking | Guidelines | Art. 21(4); 10 Jul 2027 | 2027-07-10 | None published | Not yet published | Build to the AMLR text and diary a re-check | CHK-04 | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX:32024R1624#art_21 |  | 2026-10-05
TRK-11 | Joint guidelines on partnerships for information sharing (AMLA and the EDPB) | Guidelines | Art. 75 | None | Consultation planned for the first half of 2027 | Consultation planned | Partnerships become possible on 10 Jul 2027; plan the supervisor notification and data protection impact assessment Art. 75 requires | CHK-09 | https://www.amla.europa.eu/press-release-amla-and-edpb-develop-joint-guidelines-partnerships-information-sharing_en |  | 2026-10-05
TRK-12 | RTS on central contact points | RTS | AMLD6 Art. 41(2); 10 Jul 2026 | 2026-07-10 | AMLA surveyed e-money and payment institutions until 22 Sep 2026; no draft yet | Pre-consultation engagement | Payment and e-money firms using agents in other member states: keep current central contact point arrangements |  | https://www.amla.europa.eu/news-media/news-articles/amla-launches-survey-central-contact-points_en |  | 2026-10-05

## 90-day plan
1. Window | 2. Start | 3. End | 4. Actions | 5. Owner | 6. Output | 7. Status | 8. Done date | 9. Notes
6 to 18 Oct 2026 | 2026-10-06 | 2026-10-18 | Read the three final draft standards; decide on AMLA's SDD roundtables (expressions of interest close 18 Oct); name an owner for each of the 14 workstreams | CCO, MLRO | Owner list; roundtable decision
19 Oct to 15 Nov 2026 | 2026-10-19 | 2026-11-15 | Run the article-level gap analysis for every workstream; compare the CDD data model field by field; inventory outsourced tasks against Art. 18(3); count member states for AMLA eligibility | MLRO, KYC operations, COO | Gap register with a RAG status per row |  |  | https://www.regwatch.io/blog/regulatory-change-impact-assessment-template
16 Nov to 13 Dec 2026 | 2026-11-16 | 2026-12-13 | Rebuild the BWRA methodology on the draft guidelines; size remediation by risk band; review monitoring governance against the draft guidelines; groups: identify the EU parent undertaking | MLRO, head of monitoring, group CCO | Draft methodology; remediation plan; parent decision paper
14 Dec 2026 to 3 Jan 2027 | 2026-12-14 | 2027-01-03 | Take the readiness update to the board with decisions and budget; if provisionally eligible, freeze the data set as of 31 Dec 2026; diary a re-check date for every pending AMLA instrument | CCO, CFO | Board minute; funded 2027 plan

## Changelog
1. Date | 2. Sheet | 3. Row ref | 4. Change type | 5. What changed | 6. Source URL | 7. Changed by
2026-10-01 | AMLA standards tracker | TRK-01; TRK-02; TRK-03 | Status change | AMLA published final draft RTS under AMLR Articles 28(1), 19(9), 16(4) and 17(3) and submitted them to the Commission; status set to Final draft with the Commission. | https://www.amla.europa.eu/press-release-amla-finalises-key-standards-private-sector_en | RegWatch
2026-10-02 | AMLA standards tracker | TRK-09 | Status change | AMLA invited stakeholders to sectoral roundtables on simplified due diligence (9 November to 2 December 2026; expressions of interest by 18 October 2026); status set to Pre-consultation engagement. | https://www.amla.europa.eu/amla-invites-stakeholders-sectoral-roundtables-simplified-customer-due-diligence_en | RegWatch
2026-10-05 | All | All | Structural change | Workbook created; every worked row checked against its primary source as of 5 October 2026. | https://www.regwatch.io/blog/eu-amlr-readiness-checklist | RegWatch