## READ ME
Regulatory change impact assessment template
About this template |  | Status | Instrument level | Applicability decision | Affected? | Materiality | Cost and effort band | Confidence | Yes or no
What it is for | The document a compliance team produces when a specific new rule lands: what the instrument is, whether it applies to you (with written reasoning either way), which functions and contracts it touches, and which owned, deadlined obligations fall out of it. | Draft | Level 1 legislation | In scope | Yes | High | A | High | Yes
Sheets | READ ME (this sheet, with the dropdown lists in columns D to K); Section 0 to Section 6, one tab per section of the template. Each field has a one-line instruction, a blank Your entry column and, beside it, the completed worked example for Delegated Regulation (EU) 2025/532. | In review | Level 2 delegated or implementing act (RTS, ITS) | Out of scope | Partially | Medium | B | Medium | No
Related article | https://www.regwatch.io/blog/regulatory-change-impact-assessment-template | Approved | Guidance | Partially in scope | Low | Low | C | Low
Version | Prepared by RegWatch, 30 September 2026 | Closed | Consultation | Unknown | No
Legal note | This template is general information, not legal advice. |  | Enforcement signal
How to use it
Start at final-report stage | Open the assessment when the final draft appears, not at Official Journal publication, and re-assess as the instrument moves. Log each version in Section 6.
Write the no | Record out-of-scope decisions with written reasoning and the business fact behind them. Never delete them: dismissals with reasoning are what distinguish a triage process from a guess.
Four different dates | Publication, entry into force, application and the first reporting or submission deadline are four different dates. Record each one in Section 1.
Decide the evidence now | In Section 4, name the artifact that will prove each obligation is met and how someone other than the owner will validate it.
Cite the final text | Assess against the final text on EUR-Lex or the official journal, never a summary of a draft. The worked example shows why: the rejected draft's Article 5 and the final Article 5 are different provisions.
The worked example
Scenario | A hypothetical mid-size EU payment institution whose card acquiring and processing run on ICT providers that subcontract. The organization is fictional; the regulation is real.
Instrument | Commission Delegated Regulation (EU) 2025/532, the DORA subcontracting RTS, in force since 22 July 2025 with no transitional provision for existing contracts.
Official text | https://eur-lex.europa.eu/legal-content/EN/TXT/?uri=CELEX%3A32025R0532
Facts as of | 30 September 2026, citing the final text on EUR-Lex.

## Section 0 Document control
Section 0: Document control
Field | How to fill it | Your entry | Worked example: Delegated Regulation (EU) 2025/532
Assessment ID | Sequential, for example RCIA-2025-041, referenced from your change tracker and obligations register. |  | RCIA-2025-041
Assessor | Named person, not a team. One person stays accountable for the final assessment even when many contribute. |  | Head of Compliance
Date of assessment | The date of this version. Re-assessments get new dates, logged in Section 6. |  | 7 July 2025 (v3; prior versions 12 August 2024 and 3 February 2025, see Section 6)
Status | Draft, In review, Approved or Closed. |  | Approved
Next-review trigger | A date or an event. "On publication in the Official Journal" is a better trigger than an arbitrary date for an instrument still moving. |  | Event: any ESAs guidance or Q&A on the RTS. Date backstop: first annual third-party risk review after in-force
Approver and sign-off date | Whoever owns the risk acceptance, typically the Head of Compliance or CCO. |  | CCO, 15 July 2025

## Section 1 Change identification
Section 1: Change identification
Field | How to fill it | Your entry | Worked example: Delegated Regulation (EU) 2025/532
Instrument name and official citation | Full title plus a stable identifier (CELEX number, OJ reference, Federal Register citation), never just a nickname. |  | Commission Delegated Regulation (EU) 2025/532 of 24 March 2025, an RTS specifying the elements to determine and assess when subcontracting ICT services supporting critical or important functions. CELEX 32025R0532; OJ L, 2.7.2025
Issuing authority and tier | Who made the rule and how authoritative it is (a regulation outranks a speech). |  | European Commission, on the ESAs' (EBA, EIOPA, ESMA) draft. Tier A
Instrument level or type | Level 1 legislation, Level 2 delegated or implementing act (RTS, ITS), guidance, consultation or enforcement signal. |  | Level 2: RTS under DORA Art. 30(5), supplementing Regulation (EU) 2022/2554 (Level 1, applies from 17 January 2025)
Lifecycle status | Consultation, final report, adopted, published in OJ, in force, applies, with dates for each known stage, "as of" dated. |  | In force (22 July 2025). Full history: final report 26 Jul 2024, Commission rejection 21 Jan 2025, ESAs Opinion 7 Mar 2025, adopted 24 Mar 2025, OJ 2 Jul 2025, in force 22 Jul 2025. As of 7 Jul 2025
Key dates | Publication, entry into force, application, first reporting or submission deadline. These are four different dates, and conflating them is the classic failure. |  | Publication 2 Jul 2025; entry into force and application 22 Jul 2025; no separate application date; no transitional period
Provisions changed and baseline | Which articles changed, and which earlier version you compared against. |  | New instrument; baseline is DORA Art. 30(5) and our v2 assessment of the amended draft
How detected | Source and date detected. This is the audit-trail field; the lag between publication and detection is a KPI worth tracking. |  | Daily OJ sweep, detected 2 July 2025, same day. Instrument tracked since the ESAs final report through EBA source monitoring, 26 July 2024
Change statement | One sentence: the source changes [requirement] for [regulated population or activity] in [jurisdiction] from [date], subject to [conditions or open dependencies]. If you cannot complete it yet, the development needs more legal research before it can be assessed. |  | The RTS requires DORA financial entities to assess defined elements of ICT subcontracting chains, secure specified contract content and handle provider notifications of material changes, from 22 July 2025, with no transitional provision for existing contracts, although changes to them must be made in a timely manner on a documented timeline
Worked example: Delegated Regulation (EU) 2025/532: lifecycle
Date | Event
2024-07-26 | ESAs publish the joint Final Report on the draft RTS (JC 2024 53)
2025-01-21 | Commission rejects the draft by letter: draft Article 5, on conditions across the ICT subcontracting chain, went beyond the empowerment in DORA Article 30(5)
2025-03-07 | ESAs issue their Opinion on the amended draft
2025-03-24 | Commission adopts the delegated regulation
2025-07-02 | Published in the Official Journal
2025-07-22 | In force, with no transitional provision for existing contracts

## Section 2 Applicability screen
Section 2: Applicability screen
Field | How to fill it | Your entry | Worked example: Delegated Regulation (EU) 2025/532
Entity types in scope | As defined in the instrument, cited by article. |  | Financial entities under DORA Art. 2 that use ICT services supporting critical or important functions under contracts permitting subcontracting; includes payment institutions
Our legal entities affected | By jurisdiction. A group answer is not an answer. |  | EU payment institution entity (home-state license). Non-EU group entities are out of DORA scope
Jurisdictional nexus | What ties us to the rule: establishment, licensing, customer location, employee location, data subjects, product distribution. |  | Establishment and license in the EU member state
Activities and products touched | Specific lines of business, not "operations". |  | Card acquiring and payment processing, both run on ICT arrangements classified as supporting critical or important functions in our DORA register of information
Population | Consumers, employees, counterparties or another defined group the rule protects. |  | Not applicable: a supervisory duty on the entity, not a customer-facing rule
Exemptions and proportionality | For example DORA's Article 4 proportionality principle and microenterprise carve-outs, with the provision cited. |  | DORA Art. 4 proportionality applies to how we implement; we are not a microenterprise, so no carve-out
Third parties | Whether the duty extends to outsourced services, agents, distributors or processors. |  | Yes: ICT providers and their subcontractors
Timing | Transition periods, grandfathering, phased application. |  | No transition period
Applicability decision | In scope, Out of scope, Partially in scope or Unknown, with written reasoning even when out of scope. Use Unknown when a material fact is missing, and assign an owner and a date to resolve it. |  | In scope. Reasoning: we are a DORA financial entity, and at least four ICT arrangements supporting critical or important functions permit subcontracting (cloud hosting, acquiring processing, fraud scoring, card personalization). Recorded 12 Aug 2024, reconfirmed against the final text 7 Jul 2025
Supporting business facts | The facts the decision rests on: an entity register, a licensing record, a product inventory, a threshold calculation. |  | Entity register, license record, and the four register-of-information entries flagged as supporting critical or important functions
Applicability and materiality are separate decisions. A rule can legally apply and need little work because existing controls already satisfy it; another development can impose no direct obligation and still change supervisory expectations, enforcement exposure or contract terms.

## Section 3 Impact analysis
Section 3: Impact analysis
Functions-affected matrix: a row for each function
Function | Affected? | What changes | Current-state reference (policy, control or contract)
Compliance
Legal
Procurement and third-party risk
IT and security
Operations
Finance
Front office
Check the change against eight domains, so nothing is missed
Domain | Affected? | Note
Obligations and controls (created, amended, clarified or removed)
Products and customers
Processes and operations
Data and technology
Policies and governance
People and training
Contracts and third parties
Financial or strategic effects
Rate the whole change
Field | Rubric | Your entry | Worked example: Delegated Regulation (EU) 2025/532
Materiality | High = new obligation requiring a new control or contract change. Medium = existing control needs amendment. Low = documentation or awareness only. |  | High: new obligations requiring contract changes and new due-diligence steps (rubric: new obligation plus contract change)
Urgency | Application date minus today: a mechanical calculation, not a feeling. |  | Assessed 7 Jul 2025 against in-force 22 Jul 2025: 15 days for new-contract readiness; legacy-contract exposure handled in Section 5
Estimated cost and effort band | A = documentation only. B = process or contract changes. C = new systems or controls. |  | B: process and contract changes; external counsel for addenda; no new systems
Confidence | How sure you are of the interpretation and of the business facts behind it. |  | High on scope and dates (final text on EUR-Lex); medium on how supervisors will read "well in time" in Art. 5
Judge materiality on consistent dimensions: severity if the requirement is not met, reach across entities and markets, harm to customers or the market, time available, complexity and reversibility, and the strength of existing controls. A High, Medium or Low label is only useful when its rationale is visible.
Worked example: Delegated Regulation (EU) 2025/532: functions-affected matrix
Function | Affected? | What changes | Current-state reference (policy, control or contract)
Compliance | Yes | Owns re-assessment, register updates and the evidence trail | Third-party risk policy v2.3; DORA register of information
Legal | Yes | Contract addenda for the mandatory content in Art. 4 across in-scope ICT contracts | Master services agreements; outsourcing addenda
Procurement and third-party risk | Yes | Pre-contract due diligence extended to the Art. 1 risk-profile elements and the Art. 3 risk assessment, including whether the provider can monitor its own subcontractors | Vendor due-diligence questionnaire v4
IT and security | Yes | Monitoring of subcontracting chains for critical functions; data-location tracking | Cloud governance standard; CMDB
Operations | Partially | Exit and termination playbooks extended for subcontracting failures (Art. 6) | Business continuity and exit plans
Finance | Low | Budget line for external counsel on contract remediation | Outsourcing budget FY2025
Front office | No | No customer-facing change | None

## Section 4 Obligation breakdown
Section 4: Obligation breakdown
One row per discrete obligation; this section feeds your obligations register. Decide at assessment time what artifact will prove each obligation is met, and how someone other than the owner will test that the change worked (sample, walk-through or control test).
Obligation | Provision | Owner | Deadline | Required action | Evidence that will prove compliance | Validation
Worked example: Delegated Regulation (EU) 2025/532
Obligation | Provision | Owner | Deadline | Required action | Evidence that will prove compliance | Validation
Take the elements that shape the overall risk profile and complexity of an ICT service into account when assessing subcontracting | Art. 1 | Head of TPRM | 22 Jul 2025 (new contracts) | Extend the due-diligence questionnaire with the Art. 1 elements | Revised questionnaire and completed assessments on file | Second-line sample of three new onboardings
Complete the due diligence and risk assessment before agreeing that a critical or important service may be subcontracted, including whether the provider can monitor its own subcontractors | Art. 3 | Head of TPRM | 22 Jul 2025 (new contracts) | Add the Art. 3 conditions, including a provider-oversight capability check, to onboarding due diligence | Due-diligence report section per provider | Second-line sample of three new onboardings
Ensure contracts contain the mandatory content: monitoring, data location, security standards, authority access, change notification | Art. 4 | General Counsel | New contracts 22 Jul 2025; legacy per Section 5 | Clause-gap review of in-scope ICT contracts; issue addenda | Signed addenda; clause-gap tracker | Legal spot-check of executed addenda
Handle provider notifications of material subcontracting changes ("well in time") | Art. 5 (final text) | Head of Compliance | 22 Jul 2025 | Stand up a notification-intake and response protocol with a defined assessment SLA | Notification-handling SOP; response log | Tabletop test with a mock notification
Maintain termination rights for subcontracting breaches | Art. 6 | General Counsel and Operations | 22 Jul 2025 | Extend exit plans and the termination playbook to subcontracting-triggered exits | Updated exit plans | Exit-plan walkthrough with Operations
Update the DORA register of information for subcontracting detail | DORA Art. 28(3); CIR (EU) 2024/2956 templates | Head of Compliance | Next annual register submission | Refresh subcontractor entries across the 15 register templates | Register export; submission receipt | Reconcile the register against contract records

## Section 5 Implementation plan
Section 5: Implementation plan
Field | How to fill it | Your entry | Worked example: Delegated Regulation (EU) 2025/532
Actions, owners, dates | The project plan distilled from Section 4. |  | Per Section 4; weekly stand-up owned by the Head of Compliance until all rows are green
Dependencies | Contract renewal calendars, system release windows, budget cycles. |  | Contract renewal calendar (two of four in-scope contracts renew in Q4 2025); external counsel capacity
Interim-risk acceptance | Where full compliance by the deadline is not achievable, record the interim control, its limits, who accepted the risk, when, the review cadence and the date the interim control retires. |  | The regulation has no transitional provision for existing contracts. Decision: remediate legacy contracts at renewal or within 12 months, whichever is earlier; interim exposure accepted by the board risk committee on 15 July 2025, reviewed quarterly, retired when the last addendum is signed. This is a deliberate, documented risk decision, not a grace period the regulation grants, and it matches Article 4(2), which asks for changes to existing contracts "in a timely manner and as soon as it is possible" and for the planned timeline to be documented
Post-implementation review | The date someone checks that the change achieved its intended outcome. |  | 15 January 2026: sample of new contracts and addenda checked against Art. 4, results to the risk committee

## Section 6 Sign-off & changelog
Section 6: Sign-off and changelog
A visible change log (date, change, source) for the assessment itself. Instruments move: in the worked example, the January 2025 rejection invalidated part of an assessment written in August 2024, and the changelog is how that shows.
Changelog
Date | Change | Source
Worked example: Delegated Regulation (EU) 2025/532: changelog
Date | Change | Source
2024-08-12 | v1 assessed against the ESAs final report; obligations drafted including draft Art. 5 chain-monitoring conditions | ESAs Final Report JC 2024 53
2025-02-03 | v2: Commission rejection noted (letter of 21 Jan 2025); draft-Art. 5 chain-condition workstream paused, all other workstreams continued | Commission rejection letter via EBA
2025-03-10 | ESAs Opinion on the amended draft noted; scope of the final text now stable | ESAs Opinion, 7 Mar 2025
2025-07-07 | v3 against the final OJ text: draft chain-monitoring conditions absent from the final text; "Art. 5" now denotes material-change notification. Obligations re-based; approved | EUR-Lex CELEX 32025R0532
Keep with the changelog
What to record
1 | Separate facts, assumptions and professional judgments, and record contrary views that shaped the decision.
2 | Add a review trigger whenever a conclusion depends on guidance that may change.
3 | List the events that reopen the assessment: an amendment, a correction, a final text, an interpretation by a regulator or court, local implementation, a new product, a new jurisdiction, a supplier change, an acquisition, or an assumption that turns out to be wrong.
Before approval, ask eight questions
| Question | Answer
Q1 | Is the source authoritative and current?
Q2 | Is its legal status described correctly?
Q3 | Have all relevant entities, jurisdictions, products and third parties been considered?
Q4 | Are the business facts confirmed by the people who own the activity?
Q5 | Does every significant conclusion have evidence?
Q6 | Are actions specific, owned and timed against the compliance date?
Q7 | Is validation defined?
Q8 | Are uncertainties and escalations visible?